## Sheet1
Id | Icon | Key | summary | status_SUBTASK_STATUS_CATEGORIES | timeTracking2 | customfield_10002_SUM | status_SUBTASK_STATUS_CATEGORIES_PERCENTAGE | Start Date | End Date | Parent Key | Parent Row | Link
BU-29 |  |  | Phase 1- Finding location | com.softwareplant.util.datatype.rest.ListStatusDistributionDTO@28086a9c | 0% | 7 | com.softwareplant.util.datatype.rest.ListStatusDistributionDTO@95b8e3c | 2020-09-22 | 2020-10-22 |  |  | 3FS
BU-31 |  |  | Task A | To Do | 0% | 3 | To Do | 2020-09-28 | 2020-10-05 | BU-29 | 2 | 8FS
BU-30 |  |  | Task B | To Do | 0% | 2 | To Do | 2020-10-08 | 2020-10-19 | BU-29 | 2 | 5FS
BU-32 |  |  | Select a desirable place for the model house | To Do | 0% | 2 | To Do | 2020-09-22 | 2020-10-09 | BU-29 | 2 | 11FS
BU-33 |  |  | [Milestone] Location found | To Do | 0% |  | To Do | 2020-10-12 | 2020-10-22 | BU-29 | 2 | 7FS
BU-34 |  |  | Phase 2- Designing the model house | com.softwareplant.util.datatype.rest.ListStatusDistributionDTO@45e3660f | 0% | 2 | com.softwareplant.util.datatype.rest.ListStatusDistributionDTO@61ad4bc9 | 2020-10-12 | 2020-12-09 |  |  | 19FS
BU-38 |  |  | Hire an architect | To Do | 0% |  | To Do | 2020-10-12 | 2020-10-28 | BU-34 | 7 | 27FS
BU-35 |  |  | Design utility spaces | To Do | 0% | 2 | To Do | 2020-11-02 | 2020-11-11 | BU-34 | 7 | 10FS
BU-36 |  |  | Design living spaces | To Do | 0% |  | To Do | 2020-11-12 | 2020-12-08 | BU-34 | 7 | 30FS
BU-37 |  |  | [Milestone] Model house designed | To Do | 0% |  | To Do | 2020-12-09 | 2020-12-09 | BU-34 | 7 | 12SS
BU-18 |  |  | Phase 3- Getting necessary permits | com.softwareplant.util.datatype.rest.ListStatusDistributionDTO@a9a81ea | 0% |  | com.softwareplant.util.datatype.rest.ListStatusDistributionDTO@5f65d4eb | 2021-04-21 | 2021-08-31 |  |  | 9FS
BU-11 |  |  | Prepare an ECD (Estimated Cost Breakdown) | To Do | 0% |  | To Do | 2021-04-21 | 2021-05-20 | BU-18 | 12 | 14FS
BU-4 |  |  | Secure a loan | To Do | 0% |  | To Do | 2021-04-21 | 2021-07-22 | BU-18 | 12
BU-12 |  |  | [Milestone] Purchase the property | To Do | 0% |  | To Do | 2021-07-23 | 2021-07-23 | BU-18 | 12 | 16FS, 17FS
BU-13 |  |  | Secure proper construction permits | To Do | 0% |  | To Do | 2021-07-26 | 2021-08-20 | BU-18 | 12
BU-6 |  |  | Get construction insurance | To Do | 0% |  | To Do | 2021-08-23 | 2021-08-30 | BU-18 | 12 | 6FS
BU-20 |  |  | [Milestone] Construction permits obtained | To Do | 0% |  | To Do | 2021-08-31 | 2021-08-31 | BU-18 | 12 | 15FS
BU-10 |  |  | Phase 4- Construction | com.softwareplant.util.datatype.rest.ListStatusDistributionDTO@1e81216 | 0% |  | com.softwareplant.util.datatype.rest.ListStatusDistributionDTO@a90e2e1 | 2021-06-01 | 2022-02-09 |  |  | 25FS
BU-5 |  |  | Hire builder or constructor | To Do | 0% |  | To Do | 2021-09-01 | 2021-09-10 | BU-10 | 19 | 4FS
BU-7 |  |  | Excavate the plot | To Do | 0% |  | To Do | 2021-09-13 | 2021-10-01 | BU-10 | 19 | 22FS
BU-1 |  |  | Frame the walls | To Do | 0% |  | To Do | 2021-10-04 | 2021-11-10 | BU-10 | 19
BU-39 |  |  | Check if the walls were framed according to the architect plan | To Do | 0% |  | To Do | 2021-11-11 | 2021-12-20 | BU-10 | 19 | 24FS
BU-2 |  |  | Build the roof | To Do | 0% |  | To Do | 2021-11-11 | 2021-12-03 | BU-10 | 19 | 13FS
BU-40 |  |  | Check if the roof was build according to the architect plan | To Do | 0% |  | To Do | 2021-06-01 | 2021-07-22 | BU-10 | 19 | 21FS
BU-8 |  |  | Install insulation | To Do | 0% |  | To Do | 2021-12-06 | 2021-12-15 | BU-10 | 19 | 23FS
BU-41 |  |  | Check if insulation was installed properly according to architect's plan | To Do | 0% |  | To Do | 2021-12-16 | 2022-01-03 | BU-10 | 19 | 18FS, 31FS
BU-9 |  |  | Plumb the walls and brace | To Do | 0% |  | To Do | 2021-12-16 | 2022-01-05 | BU-10 | 19 | 29FS
BU-3 |  |  | Install the exterior siding and features | To Do | 0% |  | To Do | 2022-01-10 | 2022-02-08 | BU-10 | 19
BU-19 |  |  | [Milestone] Building shell completed | To Do | 0% |  | To Do | 2022-02-09 | 2022-02-09 | BU-10 | 19 | 2FS
BU-15 |  |  | Phase 5- Interior | com.softwareplant.util.datatype.rest.ListStatusDistributionDTO@545bb788 | 0% |  | com.softwareplant.util.datatype.rest.ListStatusDistributionDTO@25e8e364 | 2022-02-10 | 2022-04-22
BU-17 |  |  | Install the wall board or panelling on interior walls | To Do | 0% |  | To Do | 2022-02-10 | 2022-02-21 | BU-15 | 31 | 33FS
BU-14 |  |  | Install plumbing fixtures | To Do | 0% |  | To Do | 2022-02-22 | 2022-03-03 | BU-15 | 31
BU-16 |  |  | Install pipes for potable water and waste drains | To Do | 0% |  | To Do | 2022-03-04 | 2022-03-24 | BU-15 | 31 | 20FS
BU-21 |  |  | Rough-in electrical outlets | To Do | 0% |  | To Do | 2022-03-25 | 2022-03-25 | BU-15 | 31
BU-23 |  |  | [Milestone] Interior finishing completed | To Do | 0% |  | To Do | 2022-04-22 | 2022-04-22 | BU-15 | 31
BU-24 |  |  | Phase 6- Installing essentials | com.softwareplant.util.datatype.rest.ListStatusDistributionDTO@64d12d6d | 0% |  | com.softwareplant.util.datatype.rest.ListStatusDistributionDTO@695b5cfc | 2022-04-25 | 2022-06-16
BU-25 |  |  | Paint the walls | To Do | 0% |  | To Do | 2022-04-25 | 2022-05-04 | BU-24 | 37
BU-26 |  |  | Install cabinets | To Do | 0% |  | To Do | 2022-05-05 | 2022-05-25 | BU-24 | 37
BU-27 |  |  | Install appliances and have the utilities turned on | To Do | 0% |  | To Do | 2022-05-26 | 2022-06-15 | BU-24 | 37
BU-28 |  |  | [Milestone] Basic interior finished | To Do | 0% |  | To Do | 2022-06-16 | 2022-06-16 | BU-24 | 37